## Sheet1
Task ID | Task Description | Responsible | Task Type | Task Status | Task Valid |  | Hours Spent | [5 empty] | Hours Remaining
[5 empty] | From | Till
1 | 2 | 3 | 4 | 5 | 6 | 7 | 1 | 2 | 3 | 4 | 5 | … | 1 | 2 | 3 | 4 | 5 | …
0 | StoryBoard | Omer | Design | Done | week1 | week2
1 | desiging Home page using HTML5+CSS | Omer | Design | In Progress
| PassengerDetails.php | Leo | Back End Done |  |  |  |  | 2
| RiskDetails.php | Leo | Back End Done | [5 empty] | 3
| ListOfFlights.php | Leo | Back End Done |  |  |  | 1
| ListOfPassengers.php | Leo | Back End Done | [7 empty] | 5
| searchPassengers.php | Leo | Back End Done | [6 empty] | 4
| searchFlights.php | Leo | Back End Done |  |  |  | 1
Total
Legend
| 4 - Task Type | Analysis, Design, Coding, Testing, Documentation, Rework, Other (Specify)
| 5 - Task Status | Not Started, In progress, Completed, Omitted, Moved into next Sprint, Split/divided, Other(specify)
| 6 - Task Valid from | Day of the Sprint when the task was defined (the consecutive number of the corresponding Daily Scrum meeting)
| 7 Task Valid Till | Day of the Sprint when the task become not valid (the consecutive number of the corresponding Daily Scrum meeting)